## Timeline
PROJECT TIMELINE
Dates | Target Today | Target For Tomorrow | Responsibility
2023-08-13 | ER Diagram + Tables Distribution +Mapping Functionality Discussion + UI Discussion + SQL Queries | UI+Study for Backend Project (Refer Youtube )-DURGESH VIDEOS | ALL
2023-08-14 | Backend Study (Durgesh )
2023-08-15 |  | Entities and Dao creation + Refer Video of durgesh and Study the whole CRUD Operation | ALL
2023-08-16 | Flow is understood | ready with task mentioned in roles and Responsibilities Tomorrow Tagret is Backend Completion
2023-08-17 | BackEnd Completion Target
2023-08-18
2023-08-19
2023-08-20 | FRONTEnd Completion Target
2023-08-21
2023-08-22
2023-08-23
2023-08-24
2023-08-25
2023-08-26
2023-08-27
2023-08-28
2023-08-29
2023-08-30

## Roles and Responsibilities
Roles and Responsibilites of Project
| TO Be completed before joining the Call | [11 empty] | Optional
S.No | Entities | Roles | Progress | Controller | Roles | Progress | Dao | Roles | Progress | Service | Roles | Progress | DTO | Roles | Progress
BaseEntity
1 | Address | Adiba |  |  | Adiba |  | Address |  |  |  | Adiba |  | Address | Adiba
2 | Cart | Adiba |  | Cart | Adiba |  | Cart |  |  | cart | Adiba |  |  | Adiba
3 | CartITem | Amber |  | CartItem | Amber |  | CartITem |  |  | CartItem | Amber |  | CartItem | Amber
4 | Category | Amber |  | Category | Amber |  | Category |  |  | Category | Amber |  |  | Amber
5 | Order | Atul |  | Order | Atul |  | Order |  |  | Order | Atul |  | Order | Atul
6 | OrderItem | Atul |  | OrderItem | Atul |  | OrderItem |  |  |  | Atul |  | OrderItem | Atul
7 | OrderStatus | Abhishek |  |  | Abhishek | [5 empty] | Abhishek |  |  | Abhishek
8 | Product | Abhishek |  | Product | Abhishek |  | Product |  |  | Product | Abhishek |  | Product | Abhishek
9 | ProductStatus | Laxmi |  |  | Laxmi |  |  |  |  | CustomUserDetails | Laxmi |  |  | Laxmi
10 | Role | Laxmi |  |  | Laxmi |  | Role |  |  |  | Laxmi |  |  | Laxmi
11 | User | Poonam |  | User | Poonam |  | User |  |  | User | Poonam |  | User | Poonam
12 | UserRole | Poonam |  | SignIn | Poonam |  | UserEntity |  |  | Image | Poonam |  |  | Poonam

## MileStones
S.No | FLOW
1 | ER Diagram
2 | Database tables
3 | backEnd Spring Boot (Controller)
4 | Frontend
5

## Tables
Table No | URBAN KART TABLES
1 | users
| user_id | email | first_name | last_name | mobile_number | password | registered_date | role_id
| PK | [6 empty] | PK
2 | address
| add_id | city | line1 | line2 | pincode | state | user_id
| PK | [5 empty] | FK
3 | roles
| role_id | role_name
PK
4 | cart
| cart_id | user_id
| PK | FK
5 | cart_items
| cart_item_id | quantity | total | cart_id
| PK |  |  | FK
6 | orders
| order_id | creation_date | order_status | total_price | user_id
| PK |  |  |  | FK
7 | order_items
| order_item_id | quantity | total_bill | product_id | user_id
| PK |  |  | FK | FK
8 | category
| category_id | category_name
PK
9 | products
| product_id | description | marked_price | product_image_path | product_name | quantity | selling_price
PK
2 | Categories
| Category ID | Category Name
PK
3 | Products List
| Product ID | Product Name | Category ID | Product Desc | Selling Price | Available Stock | Vendor ID
| PK |  | FK |  |  |  | FK
4 | Review Table
| Review ID | Customer ID | Product ID | Rating | Review | Review Date
| PK | FK | FK
5 | Vendors
| Vendor ID | Vendor Name | GST IN | Product ID (FK) | Vendor address
| PK |  |  | FK
6 | ShoppingCart Table | Temporary Table till checkout
| Cart ID | Customer ID | Product ID | Product Name | Qty | Selling Price | Total amount
| PK | FK | FK
7 | Order table
| Order ID | Product ID | Customer ID | Product Name | Vendor ID | Selling Price | Qty
| PK | FK | FK |  | FK
8 | Payment
| Customer ID | Order ID | Total Amount | Payment Mode (Cash/Online )
| PK | FK

## Login Previlges
Admin Login | All Access
User Login | For New Customer
Vendor Login | For Stock Update

## Pages
S. No | Pages Desc | Details | Access
1 | Login Page | Login Details | Admin/User/Vendor
2 | Home Page | Details of Products
3 | Listing Page | List of products(Appear After seaching the product)
4 | Cart Page
5 | Checkout/ Payment Page
6 | User Profile Page
7 | Registration Page
8 | 404 Page

## Problems
S.No | Problem
Cart ID | Mapping issues - How One Cart Id(PK) can have multiple product under it